## Data
PI | Epic | Feature | Owner | Milestone | Status | Phase | Individual progress | Progress remaining | Feature | Phase | Start Date | Days needed | Deadline | Overall progress | Days behind/ahead | Days needed(Gantt chart) | Days Complete(Gantt chart) | Feature
24.1 | SRxSN | Retrospective Dashboard | Taylor | 01 - Meeting w D&A team | Completed | HLBRs | 1 | 0 | Retrospective Dashboard | HLBRs | 4532300% | 10 | 4533700% | 100% | 0 | 14 | 14 | Retrospective Dashboard
24.1 | SRxSN | Retrospective Dashboard | Taylor | 02 - Meeting btw D&A and Busines team | Completed | HLBRs | 1 | 0 | Retrospective Dashboard | LOE | 4533700% | 10 | 4535100% | 100% | 0 | 14 | 14 | Opportunity Dashboard
24.1 | SRxSN | Retrospective Dashboard | Taylor | 04 - Submit form to LOE | Completed | HLBRs | 1 | 0 | Retrospective Dashboard | Business Requirement | 4535100% | 11 | 4536600% | 4.167% | -271 | 15 | 0.625
24.1 | SRxSN | Retrospective Dashboard | IT | 05 - Submit funding proposal to D&A | Not Required | LOE | 1 | 0 | Retrospective Dashboard | PI Planning | 4537000% | 10 | 4538400% | 0% | -259 | 14 | 0
24.1 | SRxSN | Retrospective Dashboard | Taylor | 06 - Meeting btw IT and D&A | Not Required | LOE | 1 | 0 | Retrospective Dashboard | Development | 4538400% | 60 | 4546800% | 0% | -199 | 84 | 0
24.1 | SRxSN | Retrospective Dashboard | D&A | 07 - Create new funding proposal | Not Required | LOE | 1 | 0 | Retrospective Dashboard | Business Validation | 4546800% | 5 | 4547400% | 0% | -195 | 6 | 0
24.1 | SRxSN | Retrospective Dashboard | Taylor | 08 - Submit funding proposal to business team | Completed | LOE | 1 | 0 | Opportunity Dashboard | HLBRs | 4529200% | 7 | 4530100% | 100% | 0 | 9 | 9
24.1 | SRxSN | Retrospective Dashboard | Business Team | 09 - Funding approval | Completed | Funding | 1 | 0 | Opportunity Dashboard | LOE | 4530100% | 7 | 4531000% | 100% | 0 | 9 | 9
24.1 | SRxSN | Retrospective Dashboard | Taylor | 10 - Product direction meeting btw Business and D&A | In Progress | Business Requirement | 0.25 | 0.75 | Opportunity Dashboard | Funding | 4531000% | 6 | 4532000% | 100% | 0 | 10 | 10
24.1 | SRxSN | Retrospective Dashboard | Taylor | 11 - Ensure HLBRs and BRs match | Not started | Business Requirement | 0 | 1 | Opportunity Dashboard | Business Requirement | 4532000% | 35 | 4537000% | 4.167% | -269 | 50 | 2.0833
24.1 | SRxSN | Retrospective Dashboard | Taylor | 12 -Recurring meetings btw Business and D&A | Not started | Business Requirement | 0 | 1 | Opportunity Dashboard | PI Planning | 4537000% | 10 | 4538400% | 0% | -259 | 14 | 0
24.1 | SRxSN | Retrospective Dashboard | Taylor | 13 - Meeting with product and data SME | Not started | Business Requirement | 0 | 1 | Opportunity Dashboard | Development | 4538400% | 60 | 4577800% | 0% | 24 | 394 | 0
24.1 | SRxSN | Retrospective Dashboard | Taylor | 14 - Wireframe | Not started | Business Requirement | 0 | 1 | Opportunity Dashboard | Business Validation | 4577800% | 7 | 4547400% | 0% | -195 | -304 | 0
24.1 | SRxSN | Retrospective Dashboard | Carrie | 15 - Metric definition | Not started | Business Requirement | 0 | 1
24.1 | SRxSN | Retrospective Dashboard | IT | 16 - PI planning | Not started | PI Planning | 0 | 1
24.1 | SRxSN | Retrospective Dashboard | IT | 17 - BA | Not started | Development | 0 | 1
24.1 | SRxSN | Retrospective Dashboard | IT | 18 - DF | Not started | Development | 0 | 1
24.1 | SRxSN | Retrospective Dashboard | IT | 19 - MW | Not started | Development | 0 | 1
24.1 | SRxSN | Retrospective Dashboard | IT | 20 - UI | Not started | Development | 0 | 1
24.1 | SRxSN | Retrospective Dashboard | IT | 21 - Testing | Not started | Development | 0 | 1
24.1 | SRxSN | Retrospective Dashboard | IT | 22 - IT Testing | Not started | Business Validation | 0 | 1
24.1 | SRxSN | Opportunity Dashboard | Taylor | 01 - Meeting w D&A team | Completed | HLBRs | 1 | 0
24.1 | SRxSN | Opportunity Dashboard | Taylor | 02 - Meeting btw D&A and Busines team | Completed | HLBRs | 1 | 0
24.1 | SRxSN | Opportunity Dashboard | D&A | 03 - Create business requirements | Completed | HLBRs | 1 | 0
24.1 | SRxSN | Opportunity Dashboard | Taylor | 04 - Submit form to LOE | Completed | HLBRs | 1 | 0
24.1 | SRxSN | Opportunity Dashboard | IT | 05 - Submit funding proposal to D&A | Completed | LOE | 1 | 0
24.1 | SRxSN | Opportunity Dashboard | Taylor | 06 - Meeting btw IT and D&A | Completed | LOE | 1 | 0
24.1 | SRxSN | Opportunity Dashboard | D&A | 07 - Create new funding proposal | Completed | LOE | 1 | 0
24.1 | SRxSN | Opportunity Dashboard | Taylor | 08 - Submit funding proposal to business team | Completed | LOE | 1 | 0
24.1 | SRxSN | Opportunity Dashboard | Business Team | 09 - Funding approval | Completed | Funding | 1 | 0
24.1 | SRxSN | Opportunity Dashboard | Taylor | 10 - Product direction meeting btw Business and D&A | In Progress | Business Requirement | 0.25 | 0.75
24.1 | SRxSN | Opportunity Dashboard | Taylor | 11 - Ensure HLBRs and BRs match | Not started | Business Requirement | 0 | 1
24.1 | SRxSN | Opportunity Dashboard | Taylor | 12 -Recurring meetings btw Business and D&A | Not started | Business Requirement | 0 | 1
24.1 | SRxSN | Opportunity Dashboard | Carrie | 13 - Meeting with product and data SME | Not started | Business Requirement | 0 | 1
24.1 | SRxSN | Opportunity Dashboard | IT | 14 - Wireframe | Not started | Business Requirement | 0 | 1
24.1 | SRxSN | Opportunity Dashboard | IT | 15 - Metric definition | Not started | Business Requirement | 0 | 1
24.1 | SRxSN | Opportunity Dashboard | Naazira | 16 - PI planning | Not started | PI Planning | 0 | 1
24.1 | SRxSN | Opportunity Dashboard | IT | 17 - BA | Not started | Development | 0 | 1
25.1 | SRxSN | Opportunity Dashboard | IT | 18 - DF | Not started | Development | 0 | 1
26.1 | SRxSN | Opportunity Dashboard | IT | 19 - MW | Not started | Development | 0 | 1
27.1 | SRxSN | Opportunity Dashboard | IT | 20 - UI | Not started | Development | 0 | 1
28.1 | SRxSN | Opportunity Dashboard | IT | 21 - Dev Testing | Not started | Development | 0 | 1
29.1 | SRxSN | Opportunity Dashboard | IT | 22 -BV Testing | Not started | Business Validation | 0 | 1
Formulas:
Deadline = WORKDAY([Start Date],[Days needed])
Days behind/ahead = IF(Table2[[#This Row],[Overall progress]]<100%,NETWORKDAYS(TODAY(),Table2[[#This Row],[Deadline]]),0)
Days needed(Gantt chart) = DAYS([Deadline],[Start Date])

## Pivot tables
Feature | Average of Individual progress | Average of Progress remaining | DATA LABEL | Phase | Start Date | Duration | Sum of Days Complete(Gantt chart) | Phase | Milestone | Owner | Status | Progress | Count of Status | Phase
Opportunity Dashboard | 42.05% | 57.95% | 42.05% | HLBRs | 4529200% | 9 | 9 | Business Requirement | 10 - Product direction meeting btw Business and D&A | Taylor | In Progress | 25% | Status | Business Requirement | Business Validation | Development | Funding | HLBRs | LOE | PI Planning | Status | Business Requirement | Business Validation | Development | Funding | HLBRs | LOE | PI Planning
|  |  |  | LOE | 4530100% | 9 | 9 |  | 11 - Ensure HLBRs and BRs match | Taylor | Not started | 0% | Completed |  |  |  | 1 | 4 | 4 |  | Blocked | 1 |  | 1
|  |  |  | Business Requirement | 4532000% | 63 | 2.625 |  | 12 -Recurring meetings btw Business and D&A | Taylor | Not started | 0% | In Progress | 1
|  |  |  | PI Planning | 4538300% | 14 | 0 |  | 13 - Meeting with product and data SME | Carrie | Not started | 0% | Not started | 5 | 1 | 5 |  |  |  | 1
|  |  |  | Development | 4539700% | 381 | 0 |  | 14 - Wireframe | IT | Not started | 0%
|  |  |  | Business Validation | 4577800% | 14 | 0 |  | 15 - Metric definition | IT | Not started | 0%
|  |  |  | Funding | 4531000% | 10 | 10 | Business Validation | 22 -BV Testing | IT | Not started | 0%
[8 empty] | Development | 17 - BA | IT | Not started | 0%
[9 empty] | 18 - DF | IT | Not started | 0%
[9 empty] | 19 - MW | IT | Not started | 0%
[9 empty] | 20 - UI | IT | Not started | 0%
[9 empty] | 21 - Dev Testing | IT | Not started | 0%
[8 empty] | Funding | 09 - Funding approval | Business Team | Completed | 100%
[8 empty] | HLBRs | 01 - Meeting w D&A team | Taylor | Completed | 100%
[9 empty] | 02 - Meeting btw D&A and Busines team | Taylor | Completed | 100%
[9 empty] | 03 - Create business requirements | D&A | Completed | 100%
[9 empty] | 04 - Submit form to LOE | Taylor | Completed | 100%
[8 empty] | LOE | 05 - Submit funding proposal to D&A | IT | Completed | 100%
[9 empty] | 06 - Meeting btw IT and D&A | Taylor | Completed | 100%
[9 empty] | 07 - Create new funding proposal | D&A | Completed | 100%
[9 empty] | 08 - Submit funding proposal to business team | Taylor | Completed | 100%
[8 empty] | PI Planning | 16 - PI planning | Naazira | Not started | 0%
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Branding
Colours
#5009B5
| #794CFF | #44B8F3 | #00BBBA
| #EBE4FF | #E1EDFF | #D9F5F5
#F5F5F5

## Dashboard
Phase | Milestone | Owner | Status | Progress
HLBRs | 01 - Meeting w D&A team | Taylor | Completed | 100%
| 02 - Meeting btw D&A and Busines team | Taylor | Completed | 100%
| 03 - Create business requirements | D&A | Completed | 100%
| 04 - Submit form to LOE | Taylor | Completed | 100%
LOE | 05 - Submit funding proposal to D&A | IT | Completed | 100%
| 06 - Meeting btw IT and D&A | Taylor | Completed | 100%
| 07 - Create new funding proposal | D&A | Completed | 100%
| 08 - Submit funding proposal to business team | Taylor | Completed | 100%
Funding | 09 - Funding approval | Business Team | Completed | 100%
Business Requirement | 10 - Product direction meeting btw Business and D&A | Taylor | In Progress | 25%
| 11 - Ensure HLBRs and BRs match | Taylor | Not started | 0%
| 12 -Recurring meetings btw Business and D&A | Taylor | Not started | 0%
| 13 - Meeting with product and data SME | Carrie | Not started | 0%
| 14 - Wireframe | IT | Not started | 0%
| 15 - Metric definition | IT | Not started | 0%
PI Planning | 16 - PI planning | Naazira | Not started | 0%
Development | 17 - BA | IT | Not started | 0%
| 18 - DF | IT | Not started | 0%
| 19 - MW | IT | Not started | 0%
| 20 - UI | IT | Not started | 0%
| 21 - Dev Testing | IT | Not started | 0%
Business Validation | 22 -BV Testing | IT | Not started | 0%
Rx Guide Project Tracker
88%
Complete
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
Outstanding dependencies
Notes